Federal ITS/Technology Earmark for Virginia or the Washington Metropolitan Area

ITS Projects in Northern Virginia

Quarterly Report

June 30, 2006

By

Northern Region Operations 
Planning and Programming

Changes from last report are shown in green.

Federal ITS/Technology Earmark for Virginia or the Washington Metropolitan Area

ITS Projects in Northern Virginia Summary

1.	ACTIVE Earmark Projects:	5

1.1	VDOT NOVA Projects	5

N/A	5

1.2	DC Regional Projects Administered by VDOT	5

1.2.1	FY05 $1,600,000 UPC 80889 Regional Transportation Coordination (RTC) Program (a.k.a. CapCOM)	5

1.2.2	FY01 $492,018 UPC 64861 Washington D.C. Region ITS Institutional Integration	6

1.3	DC Regional Projects Administered by Others	7

1.3.1	FY02 $1,654,637 UPC N/A Regional Integrated Transportation Information System (RITIS)	7

1.3.2	FY00 $1,600,000 FY99 $500,000 UPC N/A Capital Wireless Integrated Network (CapWIN)	8

1.4	NOVA Local Projects	9

1.4.1	FY04 $215,396 UPC TBD Tysons Corner Accelerated Traveler Information System	9

1.4.2	FY04 $353,249 UPC TBD City of Alexandria ITS Real-Time Transit Enhancement Pilot	10

1.4.3	FY02 $620,489 UPC 72744 & 70580 City of Alexandria Video Sharing	11

2.	NEAR COMPLETED Earmark Projects	12

2.1	VDOT NOVA Projects	12

2.1.1	FY04 $497,100 UPC 73136 Video Detection on Route 7 from Leesburg to Tysons Corner	12

2.1.2	FY99 $395,735 UPC 54650 Smart Traffic Center CCTV Distribution	13

2.2	DC Regional Projects Administered by VDOT	14

2.2.1	FY99 $507,348 UPC 54654 Washington DC Regional Signal Preemption and Prioritization Study	14

2.3	DC Regional Projects Administered by Others	14

N/A	15

2.4	NOVA Local Projects	15

2.4.1	FY99 $593,602 UPC 52287 Arlington County Signal Preemption / Priority on Columbia Pike	15

3.	COMPLETED Earmark Projects	16

3.1.	VDOT NOVA Projects	16

3.1.1	FY98 $250,000 UPC 51289 Tysons Corner CCTV Deployment	16

3.1.2	FY99 $200,000 UPC 54649 NOVA ITS Architecture Development	16

3.1.3a	FY98 $204,062 UPC 51286 Truck Rollover Warning system at VA 236 / Beltway	17

3.1.3b	FY98 $295,938 UPC 51286 Northern Virginia STC CCTV Quality Improvement Program (Phase I)	17

3.1.4	FY98 $133,495 UPC 51285 NOVA STC Enhancement – Beltway Detection Deployment	18

3.1.5	FY98 $1,116,505 UPC 51285 NOVA STC Enhancement – Software Enhancement and Integration	18

3.2	DC Regional Projects Administered by VDOT	19

3.2.1	FY99 $800,000 UPC 18208 Partners in Motion (PIM) Enhancement	19

3.2.2	FY96-97 $7,000,000 UPC 17272 Partners in Motion (PIM)	20

3.3	DC Regional Projects Administered by Other	21

3.3.1	FY99 $500,000 UPC N/A DC Regional Wireless Location Technology Demonstration	21

3.3.2	FY99 $200,000 UPC 54649 DC Regional ITS Architecture Development	21

3.3.3	FY99 $200,000 UPC N/A DC Regional ITS Professional Capabity Building (PCB)	22

3.3.4	FY98 $100,000 UPC51288 Regional Studies on Electronic Payment	22

3.3.5	FY98 $100,000 UPC51287 DC Regional ITS Strategic Plan	23

3.3.6	FY98 $100,000 UPC51287 ITS as Data Resource	23

3.3.7	FY98 $200,000 UPC51287 COG Staff Support to MOITS	24

3.3.8	FY98 $250,000 UPC N/A Multi-Jurisdictional Transportation Telecommunications Study	24

3.4	NOVA Local Projects	24

N/A	24

4.	INACTIVE Earmark Projects	25

4.1	VDOT NOVA Projects	25

4.1.1	FY05 $623,957 UPC TBD Reston Traffic Signal Prioritization	25

4.1.2	FY03 $623,957 UPC72659 NOVA ITS – Use VMS to Display Estimated Travel Time	26

4.2	DC Regional Projects Administered by VDOT	27

N/A	27

4.3	DC Regional Projects Administered by Others	27

4.3.1	FY98 $1,250,000 UPC N/A WMATA Tysons Corner – Bethesda Smart Bus	27

4.4	NOVA Local Projects	28

4.4.1	FY05 $1,434,617 UPC TBD Alexandria Fiber Optic Cable for Traffic Signal Coordination	28

4.4.2	FY03 $745,125 UPC 71769 Alexandria ITS King Street	28

4.4.3	FY04 $430,791 UPC TBD Fairfax County Route 1 Traffic Synchronization ITS Pilot Project	28

4.4.4	FY03 $332,777 UPC72660  Richmond Highway Transportation Improvements – Transit ITS	28

5.	Earmark Funds Not Been Claimed	29

5.1	VDOT NOVA Projects	29

N/A	29

5.2	DC Regional Projects Administered by VDOT	29

5.2.1	FY04 $430,791 UPC TBD  TBD	29

5.2.2	FY03 $1,663,884 UPC TBD  TBD	29

5.2.2	FY01 $500,000 UPC TBD  TBD	29

5.3	DC Regional Projects Administered by Others	30

Unknown	30

5.4	NOVA Local Projects	30

N/A	30

6.	Earmark Funds Were Redirected to FHWA	31

6.1	VDOT NOVA Projects	31

6.1.1	FY05 $358,654 UPC N/A  Route 7 Signalization Improvements	31

6.1.2	FY05 $717,308 UPC N/A  Route 50 Signalization Improvements	31

6.1.3	FY05 $537,981 UPC N/A  Route 28 Traffic Light Synchronization	31

6.2	DC Regional Projects Administered by VDOT	32

N/A	32

6.3	DC Regional Projects Administered by Others	32

Unknown	32

6.4	NOVA Local Projects	32

N/A	32

## ACTIVE Earmark Projects:

### VDOT NOVA Projects

#### N/A

### DC Regional Projects Administered by VDOT

#### 1.2.1	FY05	$1,600,000	UPC 80889	Regional Transportation Coordination (RTC) Program (a.k.a. CapCOM)

| Project Manager: | Doug Ham |
| --- | --- |
| VDOT Manager: | Dick Steeg |
| NOVA Coordinator: | Dick Steeg / Amy McElwain and Joe Langley |
| Project Description: | The TPB on November 17 endorsed a concept proposed by member transportation agencies to strengthen regional transportation coordination during incidents. Under the endorsed concept, an existing partnership of public safety and transportation agencies currently developing field personnel communications systems would now also address the need for regionwide communications and coordination during major transportation incidents. Since the attacks of September 11, 2001, regional leaders at the TPB and the Council of Governments (COG) have been working intensively to make sure the region is better prepared for large-scale incidents. DDOT, MDOT, VDOT, WMATA and other transportation agencies have increasingly recognized the need to address these issues on a collaborative, interagency basis. Additionally, the Greater Washington Board of Trade and others have pushed for a visible, increased level of interagency transportation coordination in the Washington region, pointing to the success of coordination by the TRANSCOM organization of New York City metropolitan area. The region received UASI and federal earmark funds to develop a Regional Transportation Coordination (RTC) Program, also known as CapCOM. |
| Status and Milestone | On-going; Drafted an agency agreement and pending on agency review and approval.. 06/2006:; Selected PB Farradyne Team as the Program Implementation Manager Team. 03/2006:; COG issued RFQ to hire a program management team. 03/2006:; Received categorical exclusion environmental certificate.. 02/2006:; FHWA approved ITS checklist template that demonstrates Rule 940 compliance. 02/2006:; CO Programming completed STIP Amendment. 02/2006:; VDOT CO Programming setup project UPC number. 10/2005:; TPB approved the TIP Amendment. 12/2004:; VDOT and GMU signed a contract to study the organizational structure. 11/2004:; TPB endorsed a concept (CapCOM) proposed by the steering committee. 05/2004:; TPB endorsed a course of action for strengthening transportation comm. & coordination during incidents.. |
| Financial Status | Funds; Amount; Balance. Earmark; 1,600,000; 1,600,000. Match by VDOT, DDOT, MDOT; 400,000; 400,000. Total; 2,000,000; 2,000,000. |

#### 1.2.2	FY01	$492,018	UPC 64861	Washington D.C. Region ITS Institutional Integration

| Project Manager: | Brien Benson, GMU |
| --- | --- |
| VDOT Manager: | Kevin Barron  David Sutton  Larry Trachy |
| NOVA Coordinator: | Amy McElwain / Joe Langley |
| Project Description: | George Mason University proposed a research project of five tasks designed to promote integration of intelligent transportation system technologies in the Washington D.C. region at an institutional level. Three of the tasks are opinion surveys, one is the calibration of the Integration traffic forecasting model to two Northern Virginia corridors, and one is a study of how ITS can facilitate the improvement of regional logistical systems. This project has five tasks: (1) Task 1 will survey user attitudes towards transportation needs in the greater Washington area, with a focus on the uses of integrated ITS. (2) Task 2 will study attitudes of elected officials in Northern Virginia towards ITS evaluation. (3) Task 3 will calibrate the Integration traffic forecasting model to the route 1 and route 7 corridors in Northern Virginia. (4) Task 4 will assess motorist attitudes towards travel time information on I-66. (5) Task 5 will explore how ITS can be used to improve regional logistical systems. |
| Status and Milestone | 07/2006:; Complete Task 5 - Final Report on ITS and Freight in the Washington Region. 06/2006:; VDOT CO granted No Cost Time Extension after resolving the mistaken overhead charge by VDOT. 06/2006:; Received exempt from full coordination through the State Environmental Review Process (SERP). 05/2006:; GMU requested a No Cost Time Extension (NCTM) to Central Office through June 30, 2007. 12/2005:; Complete Task 3 - Subtask 4:Define intersection signalization parameter. 12/2005:; Complete Task 2 - Subtask 2: Conduct pilot survey with politician. 09/2005:; Complete Task 4 - Subtask 5: Analyze survey results and prepare final report. 06/2005:; Complete Task 1. 03/2004:; Complete Task 5 - Subtask 2: Develop Survey Questions and Script. 05/2003:; VDOT signed the contract with GMU. 02/2003:; Finalized the Work Plan. 11/2002:; Formed a working group. 06/2002:; GMU submitted project application to FHWA. |
| Financial Status | Funds; Amount; Balance. Earmark; 492,018; 165,781. SPR as match; 295,211; unknown. University non-Federal funds as match; 196,807; unknown. Total; 984,036. |

### DC Regional Projects Administered by Others

#### 1.3.1	FY02	$1,654,637	UPC N/A	Regional Integrated Transportation Information System (RITIS)

| Project Manager: | Tom Jacobs  Michael Pack |
| --- | --- |
| VDOT Manager: | JR Robinson  ? |
| NOVA Coordinator: | Amy McElwain & Dick Steeg |
| Project Description: | The Metropolitan Washington region proposes to integrate existing transportation information and management systems in Virginia, Maryland, and the District of Columbia into a Regional Integrated Transportation Information System (RITIS). This project incrementally integrates data from the existing Transportation Management Centers and their associated information systems. RITIS Phase 2 supports an interface to a regional 511 system, performs improved regional integration through real-time regional data fusion, supports regional emergency preparedness planning, and enhances the information available to transportation agencies and the public for emergency response and transportation security. |
| Status and Milestone | 06/2006:; Developing a project's Concept of Operations. 02/2006:; UMD made a presentation to VDOT and COG in concluding the prototype phase.. 12/2005:; UMD completed RITIS Prototype: integrate data from WMATA, STC, MDSHA, NWS alert and generate output in various formats.. 04/2005:; Proposal and Agreement for the Development of RITIS Prototype for the D.C. Metropolitan Region was signed and fully executed by Dick Steeg on April 1, 2005. 02/2005:; Complete the deallocation of TEA-21 Section 5208 funds from VDOT to MDOT.. 12/2004:; Initiate the deobligation of TEA-21 Section 5208 funds from VDOT to MDOT.. 12/2004:; PB Farradyne completed documenting RITIS Agency Expecations and Data Sources. 07/2004:; VDOT changed PB Farradyne task to document RITIS Agency Expectations and Data Sources. 03/2004:; COG MOITS Task Force formed a 511/RITIS steering committee to manage the project. 02/2004:; VDOT tasked PB Farradyne to document RITIS data sources and COO. 09/2002:; FHWA approved the RITIS application/proposal. 09/2002:; CTB passed the resolution on the RITIS project proposal. 04/2002:; VDOT on behalf of the DC region submitted an application to FHWA. |
| Financial Status | Funds; Amount; Balance. Earmark; 1,654,637; unknown. VDOT soft match (investment in STC); 408,000; 0. MDSHA soft match (investment in CHART); 585,000; 0. VDOT CO on consultant as match; 70,913; 0. NOVA on institutional structure study as match; 21,543; 0. NOVA on RITIS development as match; 238,486; 0. MDSHA match; 330,943; unknown. DC match; 100,000; 100,000. Total; 3,409,522. |

#### 1.3.2	FY00	$1,600,000	FY99	$500,000	UPC N/A	Capital Wireless Integrated Network (CapWIN)

| Project Manager: | Tom Jacobs |
| --- | --- |
| VDOT Manager: | JR Robinson  Dick Steeg |
| NOVA Coordinator: | Pete Todd  Chris Landis  Dick Steeg |
| Project Description: | Inspired by the WWB bridge jummper incident, ITS community successfully requested ITS earmark fund to develop a project, ALERT, to improve public safety and transportation field staff communication. Previously named ALERT, now called CapWIN is a partnership between the States of Maryland, Virginia, and the District of Columbia to develop an integrated transportation and criminal justice information wireless network. This unique project will integrate transportation and public safety data and voice communication systems in two states and the DC and will be the first multi-state transportation and public safety integrated wireless network in the United States. The project can potentially also build a foundation for similar networks throughout the United States and other countries. Ultimately, CapWIN will enable transportation and law enforcement users with proper clearance the ability to readily access and use information regardless of its location in national, state, or local databases and communicate directly by data and voice. |
| Status and Milestone * CapWIN has been used to support many regional events since May 2004. | 07/2006:; Proposing exchanging data (two-way) in real-time between RITIS and CapWIN. 05/2006:; Finalized an agreement to enable data exchange between Maryland state and local public safety agencies, the Maryland Coordination and Analysis Center(MCAC) and the CapWIN. 02/2006:; VDOT and CapWIN entered into a Memorandum of Agreement arrangement.. 02/2006:; Released the new CapWIN Web Services client that included transportation data made possible by RITIS.. 05/2005:; On May 5, 2005, CapWIN began formal training of its PDA Client.. 03/2005:; On March 16, The Regional Pawn Data Sharing System (RPDSS) live and operation.. 03/2005:; On March 2, the CapWIN Executive Leadership Group (ELG) approved a recommendation to partner with the transportation community to create a Regional Transportation Coordination Program.. 12/2004:; CapWIN entered into a partnership arrangement with USDOT to begin a pilot project exploring the use of picture phones to aid transportation incident responders.. 05/2004:; 5/29 marked the 1st time the CapWIN system was used for a live event: World War II Memorial Dedication.. 03/2004:; Submitted a comprehensive Business Plan to the Executive Leadership Group (ELG) for review. 11/2003:; Roll out the Beta Test. 08/2002:; CapWIN awarded the contract to IBM Corp. 07/2001:; CapWIN received vendor proposals. 04/2001:; VDOT and CapWIN entered into partnership agreement (April 2001 - March 2002). 03/2001:; CapWIN issued RFP. 10/2000:; CapWIN implementation strategy completed and presented to the Steering Group for approval. 03/2000:; Best Practices information completed and presented to the CapWIN Steering Group. |
| Financial Status | Funds; Amount; Balance. Earmark (FY-00); 1,600,000; Unknown. Earmark (FY-99); 500,000; Unknown. National Institute of Justice; 20,638,692; Unknown. MDSHA as match; 900,000; 0. VDOT CO as match; 600,000; 0. Total; 24,238,692. |

### NOVA Local Projects

#### 1.4.1	FY04	$215,396	UPC TBD	Tysons Corner Accelerated Traveler Information System

| Project Manager: | Kathleen Jackson  ?? |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Amy McElwain / Joe Langley |
| Project Description: | TYTRAN expects to provide real time traffic information, roadway conditions, and transit information to employees and commuters in Tysons Corner that they can access through websites, email accounts, PDAs and cellular phones. |
| Status and Milestone | 07/2006:; In FY-07, VDOT increased the CCTV suiveillance camera deployment at Tysons Corner funding to $400k, but TYTRAN's project needs to catch up in order to demonstrate a soft-match by VDOT's investment. 06/2006:; Fairfax County Board of Supervisors approved the $75K matching funds request for TYTRAN's ITS grant on 6/5/06. 08/2005:; VDOT budgeted $250,000 for CCTV surveillance camera deployment at Tysons Corner which can be used as match. 07/2005:; TYTRAN members provide input on type of information should be included in this project.. 11/2004:; TYTRAN submitted project proposal to VDOT and FHWA and comments have been made available to TYTRAN.. * TYTRAN has not submitted final project proposal yet. Ms. Jackson is leaving TYTRAN.. |
| Financial Status | Funds; Amount; Balance. Earmark; 215,396; 215,396. TYTRAN Private fund as match; 80,396; 80,396. Fairfax County local fund as match; 75,000; 75,000. VDOT Investment on CCTV as soft match; 60,000; 60,000. Total; 430,792; 430,792. |

#### 1.4.2	FY04	$353,249	UPC TBD	City of Alexandria ITS Real-Time Transit Enhancement Pilot

| Project Manager: | Al Himes  WMATA |
| --- | --- |
| VDOT Manager: | JR Robinson  ??? |
| NOVA Coordinator: | Amy McElwain / Joe Langley |
| Project Description: | City of Alexandria has developed a preliminary draft scope for deploying transit traveler information but has not submitted a project proposal. FHWA had advised that this project probably should be administered by FTA. |
| Status and Milestone | 06/2005:; City would ask WMATA to act as the project manager agency. 11/2004:; Amended to TIP. |
| Financial Status | Funds; Amount; Balance. Earmark; 353,249; 353,249. City of Alexandria local fund as match; 353,249; 353,249. Total; 706,498; 706,498. |

#### 1.4.3	FY02	$620,489	UPC 72744 & 70580	City of Alexandria Video Sharing

| Project Manager: | William Haynes III  ??? |
| --- | --- |
| VDOT Manager: | JR Robinson  Kevin Barron  Ken Earnest? |
| NOVA Coordinator: | Dic Burke / Amy McElwain |
| Project Description: | This project will integrate arterial and incident management systems through the installation of CCTV on a number of key corridors, based on existing emergency routing, dynamic changes in traffic patterns, high-congestion areas, and locations with a notable history of accidents. The implementation of the CCTV system will take place in conjunction with the City-wide Fiber project, with specific focus being given to the locations selected for surveillance. These images will be controlled centrally from the City’s Traffic Control Room and shared with the Alexandria Police and Fire Departments with pan-tilt-zoom (PTZ) capability granted through a remote access request from either Department. Once this implementation of the CCTV system is complete, the distribution of these images will take place through the use of the TrafficLand application. Initially, the TrafficLand application will be implemented at a basic level to allow for regional CCTV images to be received by each of the City’s stakeholders (ATCC, AFD, APD). As the integration of the CCTV System and communications upgrades are completed, the implementation of TrafficLand will be upgraded to include the distribution of video images from the City of Alexandria to other localities. |
| Status and Milestone | 03/2006: City's project manager left in March 2006, no new pm has been designated by the city. 10/2005: City met with CO and it was determined that CO would lead this project.. 12/2004: Modifying the Draft VDOT-City Agreement. 05/2004: Approved FY04 TIP amendment. 05/2004: Finalized project scope. 01/2003: CTB resolution. 12/2002: FHWA and VDOT signed the ITS Partnership Agreement. 07/2002: Alexandria submitted the proposal to FHWA. 01/2002: FHWA notified VDOT of approved FY02 earmark fund for Alexandria, VA. |
| Financial Status | Funds; Amount; Balance. Earmark; 620,489; 620,489. RSTP federal fund; 1,220,000; 1,220,000. City of Alexandria local fund as match; 225,000; 225,000. City’s Non-federal cash, equipment, facilities, personnel services as match; 248,196; 248,196. Total; 2,313,685; 2,313,685. |

## NEAR COMPLETED Earmark Projects

### VDOT NOVA Projects

#### 2.1.1	FY04	$497,100	UPC 73136	Video Detection on Route 7 from Leesburg to Tysons Corner

| Project Manager: | Mark Hagan  Bob Sheehan |
| --- | --- |
| VDOT Manager: | Mark Hagan  Bob Sheehan |
| NOVA Coordinator: | Dick Steeg |
| Project Description: | To install video detection technology for the signal operation on Route 7 from Leesburg to Tysons Corner. Contractor completed installation of all the video detection system at 22 intersections along Route 7 on April 2005. Staff spent three months validating the quality of data collected by the video detector technology and made certain adjustments to the system by replacing loop detectors with the video detectors along Route 7 for the through traffic. The traffic signal system requires much higher detection accuracy for side street and left-turning traffic. Based on staff assessment and evaluation, loop detectors on the side streets and in turn lanes provide more accurate data than current state-of-the-art video detection for these particular situations. However, we did install the video detectors at some side streets and left-turn lanes as backup to the loop detectors. Loop detectors can easily be disturbed through repaving or construction projects and we will be able to switch to the video detectors when those types of disruptions take place but perhaps managing side street traffic less effectively. Nonetheless, a very important back up. |
| Status and Milestone | 07/2006:; Launched a 6-9 month effort to examine remaining 18 intersections associated with placement, calibration, and testing of each device. 04/2006:; Completed (4/10/06) the initial evaluation of the recommended modification scenarios began on February 15, 2006. 03/2006:; Completed reviewing scenarios with FHWA, performing field modification, and calibrating video detection units.. 03/2006:; Completed journal entry to move the charge to State fund to the RSTP federal fund.. 02/2006:; VDOT staff met with FHWA and Iteris on 2/15/06 to identify scenarios for modifications and relocations.. 02/2006:; FHWA approved our request to modify our agreement to change expenditure authorization from PE to CN.. 11/2005:; Evaluating the video detection system. 07/2005:; Completed validating the quality of data and made adjustments to the system by replacing loop detectors with the video detectors along Route 7 for the through traffic.. 04/2005:; Completed the installation of video detection at 22 of intersections along the Route 7 corridor.. 03/2005:; The contractor installed 59 of the 80 total video detection cameras & staff tested and verified the accuracy requirement.. 09/2004:; Received federal and state authorizations.. 07/2004:; Amended to July TIP.. |
| Financial Status | Funds; Amount; Balance. Earmark; 497,100; 38,264. |

#### 2.1.2	FY99	$395,735	UPC 54650	Smart Traffic Center CCTV Distribution

| Project Manager: | Gottfried Kofi  Kevin Barron  Ken Earnest |
| --- | --- |
| VDOT Manager: | Gottfried Kofi  Kevin Barron  Ken Earnest |
| NOVA Coordinator: | Jimmy Chu  Kamal Suliman  Ling Li |
| Project Description: | When VDOT embarked on an 8-year construction project to rebuild the Springfield Interchange, coordination and information sharing among various agencies impacted by the Springfield Interchange construction project became a challenge. This project was to provide video feeds from the VDOT NOVA Smart Traffic Center to the Fairfax County Police, Virginia State Police, and Partners in Motion. As the project was further scoped, it became apparent that it is much more cost-effective and beneficial to the region to expand this project to be a regional CCTV Sharing project. Toward the end of original design, the video sharing design architecture was changed to a fee-for-service option for all potential agencies in the DC metropolitan area that need to receive video images from STC. The project would include a turn-key design, installation and integration necessary for Fairfax County Police and Virginia State Police Division 7. This project is further expanded to also provide a turn-key package for WMATA after WMATA contributes funding to the project. * Original project title: Enhancing Use of CCTV Video Images for Springfield Interchange |
| Status and Milestone | 07/2006:; CO renewed the statewide contract (end of July) with Trafficland to take over NOVA STC video distribution. 12/2005:; Expect to complete the project w/ evaluation report. 10/2003:; Completed the installation for Ffx. Co. Police, VA State Police, WMATA, and Prince William Co. Police. 12/2002:; Notice of Intent to Award Trafficland. 06/2002:; VDOT issued RFP 716-WB: NOVA Video Sharing. 01/2002:; Mobility Mgmt Div. Introduced TrafficLand.com proposal as the new approach. 01/2002:; NOVA documented project status, matching status, and the change of approach to FHWA. 12/2001:; Completed original system design. 09/2000:; Expanded Scope by including Arl., Alex., P.W., MD CHART. 04/2000:; Kick-off for the original project. 02/2000:; Finalized the original project scope. 04/1999:; Submitted project proposal to FHWA. |
| Financial Status | Funds; Amount; Balance. Earmark; 395,735; -47,220. NOVA (UPC 68080); 158,400; 64,528. NOVA STC Operating Fund; 54,361; 0. CO state fund; 186,000; 0. WMATA; 72,000; unknown. CO (SPR fund for scoping); 5,000; 0. Springfield project investment as soft match; 240,000; 0. Wireless Resource Sharing goods as soft match; 172,000; 0. Total; 1,283,496. |

### DC Regional Projects Administered by VDOT

#### 2.2.1	FY99	$507,348	UPC 54654	Washington DC Regional Signal Preemption and Prioritization Study

| Project Manager: | John Collura  Hesham Rakha |
| --- | --- |
| VDOT Manager: | JR Robinson  David Sutton / Larry Trachy |
| NOVA Coordinator: | Jeris White  Mark Hagan  Amy McElwain |
| Project Description: | This project is to assist the Region in considering the use of advanced technologies to implement signal preemption and other vehicle priority strategies along signalized arterials in the Washington, D.C. Region. This project includes five major tasks: 1) Identify and review institutional issues and concerns, stakeholders, and vehicle priority needs and requirements. 2) Assess available technologies currently used in the U.S. and abroad to provide vehicle priority treatments at signalized intersections and determine the extent to which these technologies meet the vehicle priority needs/requirements in the Region. 3) Conduct an extensive simulation analysis evaluation of alternative vehicle priority strategies and treatments at signalized intersections on selected arterial(s) in the Region. 4) Conduct extensive operational field tests to evaluate alternative priority strategies and levels. 5) Develop broad guidelines to assist the region’s jurisdictions, transportation agencies, and public safety agencies in the planning and design of vehicle priority strategies and treatments along signalized arterials. These guidelines will be provided to the regional ITS Technical Task Force and the TPB ITS Policy Task Force. |
| Status and Milestone | 06/2006:; Project is considered complete and CO will pay final invoice and close the project officially. 05/2006:; MOITS Traffic Signals Group (advisory to this project) met to review and accept the project final deliverables. 04/2006:; VA Tech submitted an Executive Summary on the transit signal priority project along Route 1 Lessons Learned upon VDOT's request. 01/2006:; VA Tech submitted the Guidelines for the Planning and Deployment of Emergency Vehicle Preemption and Transit Priority Strategies. 11/2004:; VA Tech requested a no-cost extension. 07/2003:; Prepared draft guidelines for the planning and deployment of preemption/prioritization. 06/2003:; No Cost Extension to June 30, 2004. 02/2003:; Analyzed emergency vehicle accident and travel operating characteristics along Rt. 1. 02/2002:; Developed evaluation framework to use to assess performance of equipment. 07/2000:; Completed stakeholder interview and literature review. 01/2000:; VDOT signed the contract with Virginia Tech. |
| Financial Status | Funds; Amount; Balance. Earmark; 507,348; 82,607. VDOT contribution to VA Tech MAUTC as match; 120,000; Unknown. Salary from VA Tech as match; 85,472; 0. Salary from GMU Implementation Center as match; 118,203; 0. Total; 831,023. |

### DC Regional Projects Administered by Others

#### N/A

### NOVA Local Projects

#### 2.4.1	FY99	$593,602	UPC 52287	Arlington County Signal Preemption / Priority on Columbia Pike

| Project Manager: | Terry Bellamy  Valerie Lee |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Amy McElwain / Regie Beasley  Ilona Kastenhofer  Chris Reed  Dic Burke |
| Project Description: | The central goal of this project is to improve the capacity and increase operational efficiency of the Transit System and Emergency Vehicle response along Columbia Pike. The traffic signal control system will determine what type of vehicle is requesting priority and then determine what type of priority to implement. The advanced system gives the fire emergency vehicles an authorized vehicle advantage over other traffic and will provide far more efficient emergency response and provide less vehicular disruption. The major goals are to improve transit schedule adherence, increase transit rider ship, and improve the people moving efficiency of the roadway network. This project is closely coordinated with Virginia Tech that undertakes regional studies (UPC 54654), which will be helpful in defining user requirements, selecting and evaluating the Arlington County Transit, and Emergency Vehicle Preemption system. |
| Status and Milestone | 01/2006:; Arlington County granted extention to VA Tech's evalaution task to August 31, 2006. 07/2005:; Completed the evaluation scope by Wilbur Smith (lessons learned) and VA Tech (field). 01/2005:; Complete emergency vehicle and WMATA bus on-board emitter installation. 11/2004:; Complete intersection field installation. 03/2003:; Started designing the system and developing prototypes and implementation alternatives. 02/2002:; Arlington County awarded a contract to Wilbur Smith. 09/2000:; FHWA approved the work order. 08/2000:; VDOT signed an agreement with Arlington County. 04/1999:; VDOT submitted the proposal to FHWA on behalf of Arlington County. 02/1999:; FHWA informed VDOT of the designated FY99 earmark. |
| Financial Status | Funds; Amount; Balance. Earmark; 593,602; -50,599. CMAQ (partial as match); 800,000; Unknown. Arlington County local fund as match; 237,441; Unknown. Arlington County local supplementing to VA Tech Evaluation task; 50,000; Unknown. Total; 1,681,043. |

## COMPLETED Earmark Projects

### VDOT NOVA Projects

#### 3.1.1	FY98	$250,000	UPC 51289	Tysons Corner CCTV Deployment

| Project Manager: | Jeris White  Mark Hagan |
| --- | --- |
| VDOT Manager: | Jeris White  Mark Hagan |
| NOVA Coordinator: | Jeris White  Mark Hagan |
| Project Description: | The Tysons Corner area suffers from one of the highest levels of traffic congestion in the Northern Virginia region. Efforts to mitigate the effects of traffic congestion, including an express bus service provided by WMATA to serve riders between Tysons and Bethesda, MD. To support this effort, VDOT will design and install a Closed Circuit Television (CCTV) system to monitor traffic congestion and provide support for the Tysons-Bethesda transit service in the Tysons Corner area. Likewise, Montgomery County would install CCTV to monitor traffic at the Bethesda area. The system will provide video feeds to the Smart Signal Operation Center and the Smart Traffic Center and the video images would be shared with other partners including WMATA via STC CCTV Sharing mechanism. * Original scope to install 4 CCTVs, the project was completed with 1 CCTV. |
| Status and Milestone | 08/2003:; Started camera installation process on rooftop of SAIC building. 07/2002:; Secured agreement with SAIC to install cameras on rooftop. 03/2000:; VDOT reached agreement with Lerner Corporation to put CCTV on top of its building without charges. 10/1999:; FHWA approved the work order - $250,000 for design and install CCTV in the Tysons Corner area. |

#### 3.1.2	FY99	$200,000	UPC 54649	NOVA ITS Architecture Development

| Project Manager: | Amy McElwain |
| --- | --- |
| VDOT Manager: | Amy McElwain |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | Develop an architecture that regional stakeholders can easily understand and readily implement. The architecture provides a framework ("blueprint") that would drive regional decision making on transportation-related endeavors and guide NOVA operation managers through system deployment; provides general guidance and sufficient enough detail for agencies within the NOVA boundary to determine integration needs when deploying systems that are required to interface with the VDOT systems; supports neighboring ITS programs to provide transportation services to interstate travelers. This project incorporated stakeholder’s input and developed a NOVA regional ITS architecture that adheres to the USDOT policy on consistency with the National ITS Architecture and standards. |
| Status and Milestone | 08/2002:; Completed report printing and distribution. 05/2002:; Completed Architecture v1 development. 10/2001:; Follow-up outreach after 9-11. 05/2001:; Completed outreach sessions. 08/2000:; Kick off the project. |

#### 3.1.3a	FY98	$204,062	UPC 51286	Truck Rollover Warning system at VA 236 / Beltway

| Project Manager: | Jimmy Chu |
| --- | --- |
| VDOT Manager: | Jimmy Chu |
| NOVA Coordinator: | Jimmy Chu |
| Project Description: | Smart Traffic Center has been operating and maintaining two (2) Truck rollover devices that were installed in 1994. Truck Rollover warning system provides warning to trucks that are traveling too fast on the ramps in order to avoid accidental rollovers. This project is to install such a warning system on two ramps from eastbound Rt. 236 onto northbound I-495 and southbound I-495. A feasibility study on truck rollover warning system was conducted by BMI in April 1998. This project therefore will use that study and supplement with evaluating non-intrusive detection system that was not included in the 1998 study. The Truck Rollover project completed in January 2003 and the remaining ITS earmark fund was used for Northern Virginia Smart Traffic Center CCTV Quality Improvement Program on June 2004. |
| Status and Milestone | 06/2004:; Amended to the Partnership Agreement in using the remaining ITS earmark fund to improve CCTV quality. 1/2003:; Complete & activate the truck rollover warning system.. 05/1999:; Issued a task order to develop a Truck Rollover Warning System. 04/1998:; BMI completed a feasibility study on truck rollover warning system.. |

#### 3.1.3b	FY98	$295,938	UPC 51286	Northern Virginia STC CCTV Quality Improvement Program (Phase I)

| Project Manager: | Jimmy Chu |
| --- | --- |
| VDOT Manager: | Jimmy Chu |
| NOVA Coordinator: | Jimmy Chu |
| Project Description: | This project is to develop and implement a CCTV Quality Improvement Program for the Northern Virginia Smart Traffic Center. Work would focus on a subset of field devices experiencing diminished image quality and recurring operational problems. The result of this task would be an improvement in performance for this critical ITS subsystem. This project is funded by the remaining FY98 ITS earmark fund allocated to the Truck Rollover system at Rt. 236 and I-495. |
| Status and Milestone | 10/2005:; Completed 25 CCTV replacement & drafted an evaluation report. 05/2005:; Trafficland recommended solution to local control options and identified needed fund to complete the project. 06/2004:; Initiated the project in using remaining FY98 ITS earmark fund. |

#### 3.1.4	FY98	$133,495	UPC 51285	NOVA STC Enhancement – Beltway Detection Deployment

| Project Manager: | Jimmy Chu |
| --- | --- |
| VDOT Manager: | Jimmy Chu |
| NOVA Coordinator: | Jimmy Chu |
| Project Description: | The Capital Beltway in Virginia, from the American Legion Bridge to the Woodrow Wilson Bridge is void of any vehicle detection and traffic monitoring system. The deployment of ITS field equipment along the Capital Beltway has been limited to CCTV cameras at thirteen locations achieved through wireless resource sharing and as a result of congestion at the Woodrow Wilson Bridge. The purpose of this task is to develop a deployment plan for traffic monitoring detector stations along the Beltway that can be funded and installed through the wireless resource sharing program and if necessary through VDOT funding and installation. The total cost in installing detection systems on the Virginia Beltway is apprx. $2.3 million. with the funding available, this project is to implement phase 1 - install detection on the Beltway from American Legion Bridge to Dulles Toll Road. |
| Status and Milestone | 05/2002:; completed the project. 03/1999:; Issued a task order to authorize the development of a Beltway Detection Plan. |

#### 3.1.5	FY98	$1,116,505	UPC 51285	NOVA STC Enhancement – Software Enhancement and Integration

| Project Manager: | Jimmy Chu |
| --- | --- |
| VDOT Manager: | Jimmy Chu |
| NOVA Coordinator: | Jimmy Chu |
| Project Description: | The NOVA STC Integration project is to enhance the effectiveness of ITS in the Washington Metropolitan area by interconnecting some regional systems. The project consists of four elements: 1) Integration with the Virginia Smart Travel Laboratory (STL); 2) Integration with Partners in Motion; 3) Integration of Beltway Detection Sys.; 4) Evaluation of NVSTC Integration Program. |
| Status and Milestone | 09/2002:; Completed and close the project. 05/2001:; Completed 75% for integrating w/ STL.. 06/2000:; The Draft System Design Document & Requirements Document are apprx. 70% complete. 02/2000:; FHWA approved the work order - $1,087,377 for Global Resources Contract. |

### 3.2	DC Regional Projects Administered by VDOT

#### 3.2.1	FY99	$800,000	UPC 18208	Partners in Motion (PIM) Enhancement

| Project Manager: | Carol Zimmerman  Karen Cavallo Miller |
| --- | --- |
| VDOT Manager: | JR Robinson  Steve Cowherd |
| NOVA Coordinator: | Amy McElwain / Jimmy Chu / Mark Hagan |
| Project Description: | This project is to enhance how public partners input and receive data from the Partners in Motion project server. The public partners used the dial-up connection to the Agency Data Server for inputting and receiving data from the Smart Traveler system. The Agency Data Server has proven to be the least effective part of an otherwise highly successful project. An analysis of the situation, and the continuing rapid development and the use of the Internet, indicate that it would be advantageous to modify the existing system architecture to replace the Agency Data Server with Internet linking among the project partners. Also, agencies that supply a significant amount of data to the system indicated that an automatic data transmission system would be useful. |
| Status and Milestone | 06/2006:; Official project closure form, C-5, was submitted by NOVA. 10/2003:; Closed on 10/29/03.. 12/2002:; Completed (contract expired on 12/19/02). 11/2002:; Contract Modification No. 6 - contract value is increased by the total of $57,221.. 09/2002:; Formal agreement between MCDPWT and TrafficLand made on 09/20/02.. 05/2002:; Maryland Camera Distribution Subcontract letter was awarded and accepted and work commenced. 04/2002:; Contract Modification No. 4 to increase contract Value by a total of $452,188. 09/2001:; Battelle requested a no cost time extension through November 30, 2001 to allow time for VDOT to secure the required Internet connection for custom interface development.. 07/2001:; No Cost extension requested by Battelle on July 25, 2001; Extension requested through September 30, 2001 due to delays in getting the VDOT Verizon link. 05/2001:; Executed agreement with DC Emergency Services Agency for access to police, fire, rescue, and secret service information during major events for assessing impact on traffic and transit conditions.. 02/2001:; Completed Push Technology Demo. 01/2001:; 01/31/01 -- Battelle is granted No Cost Extension for Web Development, Push Technology and Custom Interfaces through July 2001.. 12/2000:; Westwood One and SmartRoute Systems merged. 10/2000:; Finalized data transformation and load of 1999 and 2000 data into the data mart and rolled out the WebTOPS (the Agency Data Server Replacement). 08/2000:; Launched Push Technology Demo. 04/2000:; Began work on Phase 2 of the Partners in Motion - the Enhancement Project by the Battelle Team. 03/2000:; Battelle received instructions from VDOT to setup an escrow account to hold the revenue-sharing funds from SmartRoute and preparations were begun to establish the account.. 02/2000:; Modified PIM contract with Battelle to replace ADS with Internet-based system.. 01/2000:; Authorized the $800,000 supplemental fund to PIM project (UPC: 17272). 03/1999:; Disconnected Agency Data Server (ADS). |

#### 3.2.2	FY96-97	$7,000,000	UPC 17272	Partners in Motion (PIM)

| Project Manager: | Carol Zimmerman  Karen Cavallo Miller |
| --- | --- |
| VDOT Manager: | JR Robinson  Steve Cowherd |
| NOVA Coordinator: | Amy McElwain / Jimmy Chu / Mark Hagan |
| Project Description: | A public-private partnership, known as Partners in Motion, was formed to implement a traveler information service for the Washington, D.C. metropolitan region. A coalition of 26 public transportation agencies and 38 planning agencies selected a team of 13 private companies led by the Battelle Memorial Institute to develop the traveler information service. This multi-modal information system enables travelers throughout the metropolitan area to have easy access to information on current travel conditions and other transportation data. |
| Status and Milestone | 06/2006:; Official project closure form, C-5, was submitted by NOVA. 08/2005:; Closed on 8/29/05.. 12/2002:; Contracted ended, COG provides a list of traveler information links on COG web site. 06/1999:; Jones Communications network will broadcast SmarTraveler TV to their subscribers in MD and VA throughout the summer. 06/1999:; GMU requests a 6 month No Cost Extension on the Evaluation of the Regional Impact of the Washington Metropolitan SmarTraveler Deployment project through 12/31/99.. 04/1999:; Seek Funding for improving Data sharing and Installing Push Technology. 04/1999:; Terminate Agency Data Server. 03/1999:; Vice President Al Gore announced that a 3 - digit number will be available for receiving travel related information. 09/1998:; WMATA placed services announcements on the outside of metrobuses and other transporation facilities. 05/1998:; Received ITS America Award. 03/1998:; Revised evaluation proposal from GMU to VDOT submitted 03/03/98 is approved with one minor modification...change the completion date to 12/31/98 from 09/30/98.. 03/1998:; Launch Agency Data Server, enabling agencies to transmit data electronically to TIC. 02/1998:; Launch SmarTraveler TV. 09/1997:; GMU submitted the 1st work order for the evaluation task: $130K to begin study and $370K to complete.. 07/1997:; Opening of Traveler Information Center (TIC), interactive telephone, and webpage services. 12/1996:; VDOT signed the contract on behalf of the DC region to develop the regional traveler Information System. |

### DC Regional Projects Administered by Other

#### 3.3.1	FY99	$500,000	UPC N/A	DC Regional Wireless Location Technology Demonstration

| Project Manager: | Dave Lovell |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Jimmy Chu |
| Project Description: | This project will demonstrate the costs and benefits of using anonymous mobile telephone call sampling technology to determine travel flow conditions throughout the Washington region. The demonstration will take place along the Capital Beltway, between the Springfield Interchange and the Maryland Route 5 Interchange. While private industry has developed a solution to the challenge of locating and tracking mobile phone calls to serve the E911 market, a variety of additional applications for this technology can be used for Smart Travel. |
| Status and Milestone | 12/2001:; U.S. Wireless Corp. filed bankruptcy and sold assets to Trafficmaster USA, Inc.. 09/2000:; Completed project evaluation. 03/2000:; Completed site planning. 11/1999:; MDSHA signed the contract with US Wireless (AW915B51). 10/1999:; Kick off. |

#### 3.3.2	FY99	$200,000	UPC 54649	DC Regional ITS Architecture Development

| Project Manager: | Andy Meese |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | This project is to perform an analysis of potential electronic information exchange for and between regional ITS applications throughout the Metropolitan Washington Area. The goal of the study is to examine the regional ITS application interface alternatives and recommend specific actions that could facilitate electronic exchange on National ITS Architecture data elements among COG member ITS applications. The development of the Metropolitan Washington Area ITS Architecture was closely coordinated with the on-going Maryland Statewide and VDOT NOVA District ITS architecture initiatives. |
| Status and Milestone | 11/2004:; Re-initiate architecture update by MWCOG staff. 062002:; Completed the development of architecture (v 1.0). 08/2000:; Issued a RFP to develop a regional ITS architecture. |

#### 3.3.3	FY99	$200,000	UPC N/A	DC Regional ITS Professional Capabity Building (PCB)

| Project Manager: | Kathy Frankle |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain / Nora Salinas |
| Project Description: | Skilled workforce is essential to effective regional ITS integration and interoperability. These funds would be provided to Universities in the region to develop and provide high priority training for those responsible. This project would offer four 3-day short courses developed by UVA, Virginia Tech, GMU, and UMD. Each course will be offered at least twice and offered at both Northern Virginia and Maryland locations. In addition, vendor-based courses would also be offered to all public and private transportation personnel in Virginia, Maryland, and the District of Columbia. Both Virginia and Maryland T2 Centers provide administrative support to this project. |
| Status and Milestone | 05/2003:; Offered the last class. 10/2000:; Offered the first class. |

#### 3.3.4	FY98	$100,000	UPC51288	Regional Studies on Electronic Payment

| Project Manager: | Sharmila Samarasinghe |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | N/A |
| Project Description: | The Regional Payment Systems Partnership project had its beginnings in inter-agency discussions within the Electronic Payment Systems Working Group (part of the ITS Technical Task Force within the Metropolitan Washington Council of Governments). The study was contracted through the Virginia Department of Transportation (VDOT) and is being managed by the Northern Virginia Transportation Commission (NVTC). The purpose of this study is to complement other electronic payments systems efforts in the region by: (1) Engaging a wide range of potential stakeholders through a sequence of interviews; (2) Identifying a longer-term vision for a multi-modal, and multiple agency system; and (3) Proposing a practical action plan that builds on the current programs and accomplishments. |
| Status and Milestone | 9/2000:; Completed. 8/1999:; FHWA approved the work order modification. 6/1999:; Kick-off the project at NVTC. 3/1999:; FHWA approved the work order. |

#### 3.3.5	FY98	$100,000	UPC51287	DC Regional ITS Strategic Plan

| Project Manager: | Andy Meese |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | The ITS Policy Task Force has recommended (meeting of June 29, 1999) and the TPB has agreed (meeting of July 21, 1999) that it was essential for the region to produce a regional strategy for ITS investments. This project also would fund consultant support for the regional ITS Architecture project. The architecture project was completed, but the Strategic Plan development project was suspended after 9/11/01, COG staff shifted the focus on emergency evacuation plan. * Another $25,000 match for this project was provided by VDOT. |
| Status and Milestone | 06/2002:; Contract ended.. 07/1999:; VDOT signed an agreement with COG. 07/1999:; TPB reached consensus the need for a regional strategy for ITS investments.. 01/1999:; FHWA approved the work order - $400,000 earmark for COG support. 02/1999:; VDOT issued a project UPC number. 01/1999:; FHWA signed the work order. 12/1998:; TPB amended FY-99 UPWP. |

#### 3.3.6	FY98	$100,000	UPC51287	ITS as Data Resource

| Project Manager: | Andy Meese |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | The development of any multi-jurisdictional data management system is not merely a technical challenge, but an institutional one. COG ITS Task Force has hired a consultant team (TransCore) to examine the feasibility of generating a multi-jurisdictional data management system. The project is scheduled in four phases: (1) study mobilization and planning; (2) inventory and assessment; (3) concept design; and (4) implementation planning. * Another $25,000 match for this project was provided by VDOT. |
| Status and Milestone | 12/2001:; Completed.. 05/2000:; Kick-off the project. 01/2000:; COG selected TransCore. 11/1999:; COG issued a RFP. 07/1999:; VDOT signed an agreement with COG. 02/1999:; VDOT issued a project UPC number. 01/1999:; FHWA signed the work order. 12/1998:; TPB amended FY-99 UPWP. |

#### 3.3.7	FY98	$200,000	UPC51287	COG Staff Support to MOITS

| Project Manager: | Andy Meese |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | * Another $50,000 match for this project was provided by VDOT. |
| Status and Milestone | 09/2001:; Agreement ended.. 07/1999:; VDOT signed an agreement with COG. 02/1999:; VDOT issued a project UPC number. 01/1999:; FHWA signed the work order. 12/1998:; TPB amended FY-99 UPWP. |

#### 3.3.8	FY98	$250,000	UPC N/A	Multi-Jurisdictional Transportation Telecommunications Study

| Project Manager: | Glenn McLaughlin |
| --- | --- |
| VDOT Manager: | JR Robinson |
| NOVA Coordinator: | Amy McElwain |
| Project Description: | The scope of this project is to: 1) Develop a detailed inventory of existing telecommunications assets utilized for ITS purposes within each MWCOG jurisdiction. 2) Analyze the inventory to ascertain the potential for connecting the disparate telecommunications infrastructures of the region. 3) Prepare recommendations and findings as a set of opportunities for interconnecting networks to form larger networks, information exchange opportunities, video sharing, etc; and 4) Document the study so that it will be useful for MWCOG jurisdictions to put forth potential projects for funding and implementation. |
| Status and Milestone | 06/2000:; Completed. 03/2000:; Presented the final draft report to COG ITS Task Force. 09/1999:; Kick-off the project. 08/1999:; MDSHA authorized CSC and PBF to conduct the study (under Network Management Services contract for all MD government agencies). 06/1999:; Appropriation of funds to MDSHA.. 10/1997:; MDSHA developed and submitted the scope of work to FHWA. |

### 3.4	NOVA Local Projects

#### N/A

## INACTIVE Earmark Projects

### VDOT NOVA Projects

#### 4.1.1	FY05	$623,957	UPC TBD	Reston Traffic Signal Prioritization

| Project Manager: | Ling Li |
| --- | --- |
| VDOT Manager: | Ling Li |
| NOVA Coordinator: | Ling Li |
| Project Description: | TBD |
| Status and Milestone | 11/2005:; 11/2005: On-hold until FHWA complete investigation on UPC 73136.. 10/2005:; Received FHWA official notice of the final award amount.. |
| Financial Status | Funds; Amount; Balance. Earmark; 537,981; 537,981. Match: TBD; 537,981. Total; 1,075,962. |

#### 4.1.2	FY03	$623,957	UPC72659	NOVA ITS – Use VMS to Display Estimated Travel Time

| Project Manager: | Amy McElwain  Kamal Suliman  Steve Brich  ??? |
| --- | --- |
| VDOT Manager: | Steve Brich  ??? |
| NOVA Coordinator: | Amy McElwain / Jimmy Chu  Kathe Jefferson |
| Project Description: | VDOT has tasked UVA, Virginia Tech, and GMU to conduct research on using NOVA STC’s existing loop sensors, using toll tag technology, and finding out user needs. NOVA intents to improve safety and reduce congestion by informing travelers with travel time information, and to measure operation efficiency in using travel time. This project will post real-time travel time information on variable message signs in Northern Virginia. The travel time information will be collected by various means such as the existing data from the Smart Tag system, installing additional toll tag readers to expand the data, and purchasing data from private sectors. The real-time travel time information should be automatically posted onto selected signs at strategic locations at all time as the default messages while incident information will have higher priority to replace the travel time information. This project is being merged with a statewide VMS travel time project and will be led by Central Office. |
| Status and Milestone | 05/2005:; Agreed to reserve the funding for participating in a statewide VMS travel time project.. 10/2004:; NOVA staff shared the draft proposal with FHWA staff for initial input and the proposal was well received.. 04/2004:; NOVA staff shared a changed project scope with VDOT staff for deploying travel time on VMS and was directed by CO to wait for research outcome.. 09/2003:; NOVA ITS manager shared a proposed project scope with VDOT staff for deploying security smart corridors - not accepted.. 04/2003:; FHWA notified VDOT of the earmarked fund.. |
| Financial Status | Funds; Amount; Balance. Earmark; 623,957; 537,981. Match: TBD; 623,957. Total; 1,247,914. |

### 4.2	DC Regional Projects Administered by VDOT

#### N/A

### 4.3	DC Regional Projects Administered by Others

#### 4.3.1	FY98	$1,250,000	UPC N/A	WMATA Tysons Corner – Bethesda Smart Bus

| Project Manager: | ??  Kathleen Donodeo  Lora Byala  Peter Meenehan |
| --- | --- |
| VDOT Manager: | N/A |
| NOVA Coordinator: | N/A |
| Project Description: | In FY1998, $1.25 million dollars of earmarked funds were reserved for WMATA to do ITS improvements on the Smart Mover project which services Bethesda and Tysons Corner. In supporting WMATA project, Montgomery County and VDOT STSS would install cameras at Bethesda and Tysons Corner for traffic monitoring. Those camera views would share with WMATA. VDOT camera views would be shared with WMATA as part of the STC CCTV Distribution project. Unfortunately, This WMATA project did not benefit a large number of people, thus with a regional effort in mind, four additional projects, which more efficiently service the area and provide a larger return on investment, were chosen. The following proposed projects will improve communication both with passengers and within the agency: (1) Touch-Screen Information Kiosk System: This project will improve passenger access to information, including transit service and traffic conditions while passengers are in Metrorail stations. (2) Line Support Information Distribution: This project will increase the real-time and static information available to employees and improve efficiency of internal administrative activities. (3) Improved Communication Links to Bus Central Control and Bus Supervisors: This project will allow the Metrobus Office of Central Control access to regional travel information, improve communication to street supervisors and improved response to street supervisors requests for and provisions of traffic information. (4) Automatic Capacity Notification at Garage: This project will provide parking information to travelers approaching Metrorail parking facilities. |
| Status and Milestone |  |

### NOVA Local Projects

#### 4.4.1	FY05	$1,434,617	UPC TBD	Alexandria Fiber Optic Cable for Traffic Signal Coordination

| Project Manager: | William Haynes III ? |
| --- | --- |
| VDOT Manager: | ?? |
| NOVA Coordinator: | Dic Burke / ?? |
| Project Description: |  |
| Status and Milestone |  |

#### 4.4.2	FY03	$745,125	UPC 71769	Alexandria ITS King Street

| Project Manager: | William Haynes III ? |
| --- | --- |
| VDOT Manager: | ?? |
| NOVA Coordinator: | Dic Burke / ?? |
| Project Description: |  |
| Status and Milestone |  |

#### 4.4.3	FY04	$430,791	UPC TBD	Fairfax County Route 1 Traffic Synchronization ITS Pilot Project

| Project Manager: | Jay Guy |
| --- | --- |
| VDOT Manager: | JR Robionson  ?? |
| NOVA Coordinator: | Bud Siegel / Amy McElwain |
| Project Description: | Fairfax County would like to combine this earmark with FY03 Richmond Highway Earmark (UPC 72660) for Signal Prioritization. No proposal has been submitted to FHWA or VDOT to date. |
| Status and Milestone |  |

#### 4.4.4	FY03	$332,777	UPC72660 	Richmond Highway Transportation Improvements – Transit ITS

| Project Manager: | Jay Guy |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Renee Hamilton  Bud Siegel / Amy McElwain |
| Project Description: | Fairfax County would like to combine this earmark with FY04 Route 1 Traffic Synchronization ITS Pilot Project for Signal Prioritization. No proposal has been submitted to FHWA or VDOT to date. |
| Status and Milestone |  |

## Earmark Funds Not Been Claimed

### 5.1	VDOT NOVA Projects

#### N/A

### DC Regional Projects Administered by VDOT

#### 5.2.1	FY04	$430,791	UPC TBD 	TBD

| Project Manager: | TBD |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Amy McElwain / Dick Steeg |
| Project Description: | Amy had mentioned to Phil, Andy and others last year (2005) that we could submit a proposal for using this fund on CapCOM as seed money. But we were busy with UASI grant proposal and later we got the SAFETEA-LU earmark for CapCOM. I am not aware of any proposal for this earmark. |

#### 5.2.2	FY03	$1,663,884	UPC TBD 	TBD

| Project Manager: | TBD |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Amy McElwain / Dick Steeg |
| Project Description: | The original idea is to fund the 2nd phase of RITIS, but then we talked about using this fund for implementing 511. We don't have a proposal for this earmark. CapWIN project manager proposed to exchange real-time data between CapWIN and RITIS and create the mobile interface for additional field data entry. |

#### 5.2.2	FY01	$500,000	UPC TBD 	TBD

| Project Manager: | TBD |
| --- | --- |
| VDOT Manager: | JR Robinson  ?? |
| NOVA Coordinator: | Amy McElwain / Dick Steeg |
| Project Description: | Email from JR Robinson dated 3/16/2001 indicating …..Relative to the DC earmark, WMATA will be submitting a proposal to FTA for $500,000 to support a regional AVL requirements effort. Corey Hill will be Virginia's contact for those funds. No proposal was submitted yet. Amy contacted WMATA’s new grant staff but no information is made available by WMATA yet. |

- In addition to existing regional efforts (RITIS, 511, CapCOM), we also have a few FY06 UASI proposals that are regional and integration in nature and may not get funded by UASI, we could use these earmark funds for. Matching is always the issue. We have not discussed ITS earmark at the MOITS Task Force for a long time; it should be a subject of discussion. I recommend the CapCOM Ad-Hoc members discuss the potential use of these earmark funds prior to the MOITS discussion.

### 5.3	DC Regional Projects Administered by Others

#### Unknown

### NOVA Local Projects

#### N/A

## Earmark Funds Were Redirected to FHWA

### VDOT NOVA Projects

#### 6.1.1	FY05	$358,654	UPC N/A 	Route 7 Signalization Improvements

| Project Manager: | Sunil Taori |
| --- | --- |
| VDOT Manager: | Sunil Taori |
| NOVA Coordinator: | Sunil Taori |
| Project Description: | To review Rt. 7 corridor traffic issues and implement ITS solutions and signal improvement measures. Congressman Wolf’s expectation is to deploy more video detection to this corridor after a review of the FY04 video detection deployment on Rt. 7 (UPC 73136). |
| Status and Milestone | 02/2006: Earmark Fund was re-directed to FHWA.. 11/2005: On-hold until FHWA complete investigation on UPC 73136. 10/2005: Received FHWA official notice of the final award amount.. |

#### 6.1.2	FY05	$717,308	UPC N/A 	Route 50 Signalization Improvements

| Project Manager: | Sunil Taori |
| --- | --- |
| VDOT Manager: | Sunil Taori |
| NOVA Coordinator: | Sunil Taori |
| Project Description: | To review Rt. 50 corridor traffic issues and implement ITS solutions and signal improvement measures. Congressman Wolf’s expectation is to deploy video detection to this corridor after a review of FY04 video detection deployment on Rt. 7 (UPC 73136). |
| Status and Milestone | 02/2006: Earmark Fund was re-directed to FHWA.. 11/2005: On-hold until FHWA complete investigation on UPC 73136. 10/2005: Received FHWA official notice of the final award amount.. |

#### 6.1.3	FY05	$537,981	UPC N/A 	Route 28 Traffic Light Synchronization

| Project Manager: | Sunil Taori |
| --- | --- |
| VDOT Manager: | Sunil Taori |
| NOVA Coordinator: | Sunil Taori |
| Project Description: | To review Rt. 28 corridor traffic issues and implement ITS solutions and signal improvement measures. Congressman Wolf’s expectation is to deploy more video detection to this corridor after a review of FY04 video detection deployment on Rt. 7 (UPC 73136). |
| Status and Milestone | 02/2006: Earmark Fund was re-directed to FHWA.. 11/2005: On-hold until FHWA complete investigation on UPC 73136. 10/2005: Received FHWA official notice of the final award amount.. |

### 6.2	DC Regional Projects Administered by VDOT

#### N/A

### 6.3	DC Regional Projects Administered by Others

#### Unknown

### 6.4	NOVA Local Projects

#### N/A