## Summary
MWAQC 8-Hour Ozone Planning Schedule
SIP Planning and Transportation Conformity Determinations
DRAFT December 15, 2004
|  |  | Fall 2004 | Winter 2004 | Spring 2005 | Summer 2005 | Fall-Winter 2005 | Spring-Sum 2006 | Winter 2006 | Spring 2007
[11 empty] | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01
Control Measure Development
Preliminary identification of new local measures
Preliminary identification of regional controls (reduce transport)
Adopt local control regulations
Modeling Analysis
Set-up, testing
Strategy analysis
ROP / 15% Plan Analysis
Preliminary Analysis
SIP demonstration
Inventory Development
2002 Base Year
Projection year for ROP
Modeling inventories for attainment
Conformity
Complete final 1-hour conformity
Complete 8-hour conformity FY2005-2010 TIP
Complete 8-hour conformity FY2006-2011 TIP
Develop 8-hour mobile budgets(SIP)
SIP Submittal
Reasonable Further Progress SIP
Submittal to EPA: due 12/31/06
Prepare draft Attainment SIP
Submittal to EPA: due June 15, 2007
Note: | This schedule is uncertain, pending release of additional EPA guidance in March 2005 requirements for meeting the 8-hour standard. This schedule will be revised once the additional guidance is issued.