## Sheet1
MWAQC 8-Hr SIP Schedule, October-April 2007
9/13/06
Date | Meeting | Agenda | SIP Action | Other action
Sept
12 | TAC | Updates
27 | MWAQC | Updates |  | 2007 CLRP conformity
Oct
10 | TAC | Review conformity letter | Recommend
19 | Stakeholder | Input on control strategy
25 | MWAQC | Local Commitments to SIP | Briefing | appoint nominating ctte
Nov
7 | TAC | Draft SIP | Review and comment | Receive IAQC input
15 | MWAQC | Final modeling results, WOE | Briefing | elect officers for 2007
Dec
5 | TAC | SIP changes
13 | MWAQC* |  |  | elect officers for 2007
Jan
9 | TAC | Draft SIP (rev) | Recommend for public comment
24 | MWAQC | Draft SIP | Approve for public comment
Feb
6 | TAC
| Public Hearings | Public Hearings
Mar
6 | TAC | Response to comments
28 | MWAQC | FY 08 Budget & work program | Approve FY 08 work program/budget | New member orientation
| Public Hearings | Public Hearings
April
10 | TAC | Response to comments | Recommend SIP approval
25 | MWAQC | SIP, Response to comments | Approve SIP, send to states
May
| States | IAQC, States review SIP | States submit SIP to EPA by 6/15/05