## Sheet1
Task/Step |  | Lead | 3/19-3/23 | 3/26-3/30 | 4/2-4/6 | 4/9-4/13 | 4/16-4/20 | 4/23-4/27 | 4/30-5/4 | 5/7-5/11 | 5/14-5/18 | 5/21-5/25 | 5/28-6/1 | 6/4-6/8 | Jun-Dec
1 | Recognition of Founding Members
1.1 | Signature Event
a | Confirm date (6/5/07 3:00-5:00 pm) | Harriet | x
b | Confirm location | Harriet | x
c | Compile invitation list | Barbara Jen |  | x
d | Finalize list of Founding Members | TBD |  | x
e | Sent out "Save the Date" email | Jen |  |  | x
f | Design/print formal invitation | Jen |  |  | x | x | x | x
g | Mail formal invitation | Jen | [6 empty] | x
h | Prepare agenda | Harriet |  |  | x
i | Prepare joint agreement | Harriet |  |  | x
j | Select/order commemorative item(s) | Jen |  | x | x
k | Select/order gift for Founding Members | Jen |  | x | x
l | Get quotes from caterers | Jen |  |  |  | x | x
m | Select caterer and menu | Jen |  |  |  | x | x
n | Order rental equipment (if required) | Jen |  |  |  | x | x
o | Select/order flower arrangements (?) | Jen |  |  |  | x | x
p | Send event reminder email | Jen | [10 empty] | x
q | Confirm F&B, equipment orders | Jen | [10 empty] | x
r | Set up/conduct event | All | [11 empty] | x
1.2 | Hall of Fame/Tree Planting | TBD
a | Select location(s) | TBD
b | Select/order plaque | TBD
c | Select.order tree(s) | TBD
d | Coordinate scheduling | TBD
e | Invite participants | TBD
f | Conduct event | TBD
1.3 | Media Recognition | TBD
a | Feature founding members in 2007 media campaign | PRR |  |  | x | x | x | x | x | x | x | x | x | x
2 | National Leadership
2.1 | Proclamations (DC, MD, VA)
a | Draft proclamations | TBD |  |  | x | x | x
b | Get signed | TBD | [5 empty] | x | x | x | x
c | Have framed | TBD | [9 empty] | x | x
2.2 | Awards
a | Identify award(s) | Harriet
b | Submit application(s) | Jen
3 | Alignment with Others
3.1 | Recruit New Partners
a | Identify new partners | PRR | x | x | x | x | x | x | x | x | x | x | x | x | x
b | Contact prospects | PRR | x | x | x | x | x | x | x | x | x | x | x | x | x
c | Obtain new partners | PRR | x | x | x | x | x | x | x | x | x | x | x | x | x
Task/Step |  | Lead | 3/19-3/23 | 3/26-3/30 | 4/2-4/6 | 4/9-4/13 | 4/16-4/20 | 4/23-4/27 | 4/30-5/4 | 5/7-5/11 | 5/14-5/18 | 5/21-5/25 | 5/28-6/1 | 6/4-6/8 | Jun-Dec
4 | Marketing & Outreach
4.1 | Clean Air Partners' Time Line
a | Compile information for Time Line | Barbara
b | Create Time Line | PRR
4.2 | "Faces of Clean Air" Web Clip |  | INSUFFICIENT FUNDING
4.3 | Engaging the Public | Harriet
a | Draft contest guidelines/application |  | x | x
b | Get sponsors for give aways |  |  |  | x | x | x | x | x
c | Promote through web site | [8 empty] | x | x | x | x | x | x
d | Make awards | [13 empty] | x