| Meeting Date | MWAQC-TAC | MWAQC Mtgs/Worksessions | Deliverable | Conformity Schedule |
| --- | --- | --- | --- | --- |
| Jan 21 – TAC | -Control Measure Priorities -Emissions Inventory Development |  |  |  |
| February 11 – TAC 23 – MWAQC* | -Emissions Inventory Development -Control Measure Analysis -Draft FY06 program of work | Regular Meeting: -Emissions Inventory Development -PM Designation Briefing:: FY2006 Work Program and Budget |  | Comments to TPB on MOBILE6.2 input revisions for 8-hour conformity |
| March 11- TAC | -FY2006 Work Program and Budget -RFP Inventory, 2008 Control Measures Priority Emiss. Reductn Requirements |  | *RFP Inventory 2008 *Early Action Control Measure Report |  |
| April 8- TAC 27-MWAQC* | -RFP Inventory, 2008 -Priority Control Measures -Attainment Modeling Group meets Modeling Inventory | Regular Meeting: IAQC Transmittal/ Consideration Action: FY2006 Work Program and Budget | *Draft Control Measure Prioritization Report |  |
| May 13-TAC 25-MWAQC | -Attainment Modeling report -RFP Inventory, Analysis -Priority Control Measures | Strategic Planning Session Review Priority Control Measures |  |  |
| June 10– TAC 17 - MWAQC | -RFP Analysis, 2008 -Modeling:Strategy Analysis | Strategic Planning Session: Action: Approve Draft Control Strategy | *Emissions Reductions Requirements 2008 *Final Control Measures Priorities Report |  |
| July 8 – TAC 27 – MWAQC* | -RFP Analysis, 2008 -Modeling Strategy Analysis -Conformity FY06-2011 | Regular Meeting: Action: Comment on 8-hour Conformity for FY06-2011 | *Preliminary Control Strategy Report | Comment on Air Quality Conformity Determination for 2005 CLRP and FY2006-2011 TIP |
| August | No meeting | No meeting |  |  |
| September 9 – TAC 28 – MWAQC* | -Emissions Inventory for 2008,2009 -Modeling Strategy Analysis -Prelim. Control Strategy | Regular Meeting: Action: Approve Preliminary Control Strategy for public meetings | Public meetings on preliminary control strategy | TPB adopts Air Quality Conformity Determination for 2005 CLRP and FY2006-2011 TIP |
| October 14 – TAC 26 - MWAQC | -Emissions Inventory for attainment, 2009 -Control Measure Develop. | Strategic Planning Session: Action: Approve Status Report on Attainment Modeling | *Status Report on 8-Hr Ozone Inventories and Photochemical Modeling |  |
| November 10 – TAC 16- MWAQC* | Emissions Inventory for attainment, 2009 Draft 8-Hr Ozone SIP Template | Regular Meeting: Action: Approve Draft 8-hr ozone SIP template (RFP analysis) |  |  |
| December 9 – TAC | -RFP Analysis, 2008 -Projection Inventory2009 |  | Draft 8-Hour Ozone SIP Template |  |

| Meeting Date | MWAQC-TAC | MWAQC Mtgs/ Worksessions | Deliverables | Conformity Schedule |
| --- | --- | --- | --- | --- |
| January 2006 13 – TAC | Attainment Inventory Report Schedule for Attainment SIP |  |  | Conformity for PM2.5 |
| February 10- TAC 22 - MWAQC | Review Draft SIP Review Proposed MWAQC Budget, FY 2007 | Strategic Planning Session: TBD | Draft SIP to TAC |  |
| March 10- TAC 22 – MWAQC | TBD | Regular Meeting: Draft SIP to MWAQC, Approve for Public Comment Action: Approve MWAQC Budget FY2007 | SIP Approved for Public Hearings |  |
| April 14 – TAC | TBD | Public Hearings |  |  |
| May 12 – TAC 24 - MWAQC | TBD | Strategic Planning Session: Review Public Comment and Response to Public Comment |  |  |
| June* 9 – TAC 28 - MWAQC | Review Response to Public Comment | Regular Meeting: Action: Approve Responses to Public Comment and SIP |  |  |
| July* 14 – TAC 26 - MWAQC | Review SIP, Recommend to MWAQC | Regular Meeting: Action: Approve SIP to send to States | MWAQC Approves SIP* |  |

* Depending on the timing of public hearings, the MWAQC will meet in either June or July to approve the SIP.