## Summary
MWAQC 8-Hour Ozone Planning Schedule*
SIP Planning and Transportation Conformity Determinations
DRAFT April 8, 2005
ITEM 6
|  | Fall 2004 | Winter 2004 | Spring 2005 | Summer 2005 | Fall-Winter 2005 | Spring-Sum 2006 | Fall-Winter 2006 | Spring 2007
[10 empty] | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01
Control Measure Development
Preliminary identification of new local measures
Preliminary identification of regional controls (reduce transport)
Adopt preliminary control strategy
Public Meetings on control measures
Adopt control strategy
Modeling Analysis
Set-up, testing
Finalize protocol document
Strategy analysis
Complete attainment modeling
Inventory Development
2002 Base Year
Projection year for ROP 2009
Prelim. Emission Reduction Requirements
Modeling inventories for attainment
Conformity
Complete final 1-hour conformity
Complete 8-hour conformity FY2005-2010 TIP
Complete 8-hour conformity FY2006-2011 TIP
Develop 8-hour mobile budgets(SIP)
SIP Submittal
Public Meetings on control strategy
Draft SIP Template
Prepare Draft Attainment SIP/Regl Air Quality Plan
Adopt Draft Attainment SIP (MWAQC)
Public Hearings
Approve SIP/Regional Air Quality Plan (7/06)
States Submit SIP to EPA 9/06
SIP Deadline: June 15, 2007
*Note: | This schedule is uncertain, pending release of additional EPA guidance and requirements for meeting the 8-hour standard. This schedule will be revised once the additional guidance is issued.