## Sheet1
MWAQC 8-Hr SIP Schedule, October-April 2007
Proposed 9/12/06
Date | Meeting | Agenda | SIP Action | Other action
Sept
12 | TAC | Updates
27 | MWAQC | Updates |  | 2007 CLRP conformity
Oct
10 | TAC | Draft SIP (w/o final modeling results) | Review & comment
19 | Stakeholder | Input on control strategy
25 | MWAQC | Final modeling results | Briefing
|  | Local Commitments to SIP | Receive/approve | appoint nominating ctte
Nov
7 | TAC | Draft SIP (rev)
15 | MWAQC | Draft SIP (rev) | Approve for public hearing | elect officers for 2007
Dec
5 | TAC
13 | MWAQC
Jan
9 | TAC
Public hearings
Feb
6 | TAC | Review, corrections
28 | MWAQC | Response to comments | Approve
Mar
6 | TAC | Review response to comments
Recommend final SIP
28 | MWAQC | Approve final SIP
April
10 | TAC
25 | MWAQC