ITEM #5

COMMUTER CONNECTIONS TERM EVALUATION SCHEDULE

TARGET DATE:	JUNE 2008

Measure			Data Collection		Deadline(s)			Est. Contractor	FY Completion

Activity							Cost

Telework 			2007 State of the 		January 2007					FY07 and FY08

Commute

Employer Survey		January 2008		$5,000		FY08

Employer Outreach		Database Information	December 2007		$9,500		FY08

From ACT!

GRH				In-depth GRH applicant	January 2007		$20,000		FY07

Survey

Commuter Operations	Placement Rate Study	July – September 2005	$15,000		FY06

Center		3rd Quarter			(COMPLETED)

Survey by Oct/Nov 2005

Marketing			State of the Commute	January 2007					FY07 & FY08

Bike To Work Day 		2007 Participant Survey	Nov/Dec 2007		$4,000		FY08

InfoExpress Kiosk		2007 State of the		January 2007					FY07 & FY08

Commute

ALL				Regional State of the	January 2007		$400,000		FY07 & FY08

Commute Survey

Measure		Data Collection		Deadline(s)					FY Completion

Activity

ALL				2005 TERM Analysis	January 2006		$25,000	FY06

Report			(COMPLETED)

ALL				2006 - 2008 TERM  	January 2009		$25,000	FY09

Analysis Report

ALL				TDM Evaluation 		December 2006		$25,000	FY07

Framework Methodology

- FY06 = July 1, 2005 – June 30, 2006

- FY07 = July 1, 2006 – June 30, 2007

- FY08 = July 1, 2007 – June 30, 2008

# TDM Evaluation Project Cost Estimates

Total Estimated Contractor Costs*

FY06		$45,000

FY07		$350,000

FY08		$68,500

Estimated Overall Commuter Connections Budget:

FY06 		$6.0 M

FY07		$6.0 M

FY08		$4.5 M

Percent of FY Budget

FY06		<1%

FY07		6%

FY08		1.5%

*Although COG/TPB staff, indirect and direct costs and data and PC costs are not included in the contractor cost, the costs for these line item  categories are already included in the CCWP Monitoring and Evaluation program element budgeting projections.  These are CCWP activities that would normally occur and have already been budgeted in the overall tasks and product deliveries.  Costs shown are estimates and may fluctuate due to contractor pricing, market place changes, and program demands.